## Sheet1
Author | Malcolm Knapp
Date | 2017-05-17
Project | Arduino DDS Extension
Reviewer | Document | Version | Issue | Suggestion | Documentation Updated | Issue | Documentation Updated
Malcolm Knapp | Product Definition | 2b6f39 | versioning on file name is unecessary | github handles versioning so you can delete that. | Documents name changed to Product Definition.txt
Malcolm Knapp | Product Definition | 2b6f39 | The extra space looks messy | Remove extra spaces | Extra spaces removed
Malcolm Knapp | Product Definition | 2b6f39 | misspelled words | It is easy to do a spell check so do one before you submit | Spell checker run
Malcolm Knapp | Product Definition | 2b6f39 | "- State one passes signal from LPF to the Attenuator - State two passes signal through EQ. " is capture by the Flow Diagram | remove from the text file | Text removed from the file
Malcolm Knapp | Product Definition | 2b6f39 | " - Variable resitors on each filters output to control amplitude " Why do you need this when there is a master Attenuator? | Determine if they are redundent or not | Not redundent. Vocabulary is changed to make it more clear. Variable resistors attached to each filters output to control the individual band amplitude
Malcolm Knapp | Product Definition | 2b6f39 | On the BLE the " 3.3V input" over is an over definition. | Determining voldtage for components usually can happen in the Architecture phase. You may end up finding a module that runs off 5V and so you would then have to change the this definition. What you are looking for is information that will not change throughout the how development | Removed the 3.3V
Malcolm Knapp | Product Definition | 2b6f39 | Phone Interface - Is this an inferface on a feature? | if it is an interface then move it to that section | Removed because it is not a feature, application would be a feature.
Malcolm Knapp | Product Definition | 2b6f39 | Do you just need a phone to communicate? | Think about what other things you need to communicate with a phone | Removed phone. Replaced with computer and wire to arduino
Malcolm Knapp | Product Definition | 2b6f39 | "- Wire from header to chip" is a lower level detail | you do not need to show this at the Product Definition level. You will get into that at the Architecture level | Removed the detail.
Malcolm Knapp | Product Definition | 2b6f39 | "- Must be modern version of bluetooth" is vague | How a about must be "Bluetooth Version > ???" | Removed the Bluetooth module
Malcolm Knapp | Product Definition | 2b6f39 | " State: Eq switch off The State Switch has been deactivated" I am unclear how the state are organized between the two switches. Are they parallel states or do they interact. | Clarify what you mean by this | Changed to "The Switch is in position 0" and the atates are in parallel
Malcolm Knapp | Product Definition | 2b6f39 | "FEATURE 3 Shield Connection" is describing an interface not a Feature | move it to the feature section and combine it with the Bluetooth Interface | Shield connection is moved into the interface section
Malcolm Knapp | Product Definition | 2b6f39 | "FEATURE 4 Arduino Channel Selector" characteristics does not match flow diagram | Decide on what connections you want and update the appropriate places | Multiple signals from the arduino are split between separate channels.
Malcolm Knapp | Flow Diagram | 2b6f39 | It is a little cramped | In Inkscape you have an infinite page so you it to make your flow diagrams easy to read. Align the main signal in one row and then have the secondard signal come off of that. See 012916 Flow Diagram Organization for details | More spaces added. | What I was trying to get at was to align and organize the block diagram so it is easier to read.
Malcolm Knapp | Flow Diagram | 2b6f39 | FOR ALL other notes see Feature Block Diagram Rev_3_5-16-2017 - MK Comments |  | Comments addressed
Malcolm Knapp | Flow Diagram | 2b6f39 | No computer block | add this block | Added computer block
Malcolm Knapp | Flow Diagram | 2b6f39 | EQ switch called Switch | Synchronize Names | Synchronized to EQ sqitch
Malcolm Knapp | Flow Diagram | 2b6f39 | Connection between BLE and microcontroller missing | Add Connection | Reomved the BLE module
Malcolm Knapp | Flow Diagram | 2b6f39 | Code flow diagram is missing | Add Code Flow diagram for Tone to DDS path | Product definition Product States is text version of code flow | The flow of information in within the ATTiny has not been enumerated yet
Malcolm Knapp | All docs | cbdf8ef | Auther, date etc not updated | Make sure you update author and date
Malcolm Knapp | Major Signals | cbdf8ef | "Arduin pin XX" is not descriptive. Same with LED Signal | Choose a more descrptive name
Malcolm Knapp | Major Signals | cbdf8ef | Are you sure the DDS signal max freq is 50Khz?
Malcolm Knapp | Major Signals | cbdf8ef | Make sure that max frequency is what you are calling out and not fundamental | Adjust as needed
Malcolm Knapp | Major Signals | cbdf8ef | Why is the LED Signal frequecny 20Hz
Malcolm Knapp | Major Signals | cbdf8ef | Arduino Output Signal | Do you mean the Tone Signal?
Malcolm Knapp | Interface List | cbdf8ef | "Dip_1, Dip_2, etc" are not descriptive names | Choose a more descriptive name for this signal
Malcolm Knapp | Interface List | cbdf8ef | Attiny does not have all pins called out | Add missing pin out
Malcolm Knapp | Interface List | cbdf8ef | Pin Numbers are not numbers | Replace with number. The INTERFACE NAME is where you put the connector name and when you do choose a descriptive name
Malcolm Knapp | Current Budget | cbdf8ef | Why does the EQ pull current
Malcolm Knapp | Major Components BOM | cbdf8ef | LED is available from mouser. | Can you get it from Mouser or do you need to get it from Digikey
Malcolm Knapp | Major Components BOM | cbdf8ef | Speaker is .1W but Speaker Single in is .125W | Will this be a problem?
Malcolm Knapp | Major Components BOM | cbdf8ef | Lots of parts are through hole. How will that impact manufacturabiility | Surface mount parts are easier to use with a milled board so consider that when choosing parts
Malcolm Knapp | Major Components BOM | cbdf8ef | Speaker has a bandwidth of 200Hz to 20KHz not 20Hz to 20KHz | Is that a problem?
Malcolm Knapp | Calculations | cbdf8ef | Caluclations are not specific | Make eachcalculations speicific. It is fine to duplicate the equations. This means if something changes you do not destroy information used by other parts of the design
Malcolm Knapp | Calculations | cbdf8ef | Amplifier Calculations. How much applification are you planning to have | Add Calculations
Malcolm Knapp | Calculations | cbdf8ef | Filter loading calculations. How much signal loss happens in the filters | Add Calculations
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | Overall great job on this diagram. Is a easy to read and well laid out
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | Major signal names missing | Add the major signal names
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | How will the ATTINY be programed | Add a programming method
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | There is no master volume control in this diagram. | Is that intensional?
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | how will the 3 band EQ be implemented. If it is in separate filters thet should be shown as separate blocks | Add blocks as needed
Malcolm Knapp | Flow Diagram | d7b8fe0 | Is the state Indicator Conrtrolled by the State Switch as shown in the Flow diagram or is controled by the micro as shown in the hardware block diagram | Clarify which on is correct
Malcolm Knapp | Flow Diagram | d7b8fe0 | Master volume block does not appear in this diagram | add it to match HWBD
Malcolm Knapp | Hardware Block Diagram | d7b8fe0 | Great organization :) It is really easy to follow the signal flow
Malcolm Knapp | Hardware Block Diagram | d7b8fe0 | What block on the Flow diagram does the ON/OFF switch map to?
Malcolm Knapp | Hardware Block Diagram | d7b8fe0 | Physical Pin interface and Master Volume do not name something you can buy. | Rename them to something you can phyiscally get. i.e. how will you implement those two blocks
Malcolm Knapp | Hardware Block Diagram | d7b8fe0 | For signals that go to the same I/O, such as PB1, should be shown connected. | Redraw siganl to show the connection. This also implies that the pin must be able to operate correctly no matter what signal is flowing through it. For example have you made sure that the ON.OFF switch will not interfere with the programming
Malcolm Knapp | Hardware Block Diagram | d7b8fe0 | How does the power flow through the POT, On/Off Switch and LED.
Malcolm Knapp | Interface Pinout | d7b8fe0 | DDS Pin Interface / DIP Switch is not part of the connector so you do not need to enumerate it here. These connection will be capctured by the schematic
Malcolm Knapp | Major Signals list | d7b8fe0 | Are you sure the max frequency is for the DDS Tone Output Signal is 32KHz
Malcolm Knapp | Major Signals list | d7b8fe0 | Add the Type for each major signal (analog, digital , PWM etc) | This makes it easier to understand for the reader. A 1KHz sine wave is different than a 1kHz PWM
Malcolm Knapp | Calculations | d7b8fe0 | Complete the loss calculations for the ChebyShev and RC filter. This will give you an idea how much amplification you will need.
Malcolm Knapp | Product Definition.txt | d7b8fe0 | Update Introduction to reflect the current state of the project
Malcolm Knapp | Product Definition.txt | d7b8fe0 | Chebyshev Low pass filter: "Line Loss must be less than ??100MW??" | Do you mean 100mW
Malcolm Knapp | Product Definition.txt | d7b8fe0 | Amplifier: "200 MW of current" | You should use amp for current and watts for power. So do you mean "200 mW of power"?
Malcolm Knapp | Product Definition.txt | d7b8fe0 | "State: Idle State Event: Micro Controller is set to Idle" Events that where nothing happens can be removed | remove this event
Malcolm Knapp | Product Definition.txt | d7b8fe0 | "State: Arduino Frequency Signal Driven State Event: Input is received". Input is received is a vague statement | Clarify what you mean
Malcolm Knapp | Product Definition.txt | d7b8fe0 | " # The selector connects the chosen Arduino Channel to the micro-controller " is a characteristic not a behavior | Move to characteristics list
Malcolm Knapp | Product Definition.txt | d7b8fe0 | Output Signal Controlling States State: EQ slide switch in position A Event: The Switch is in position A # Signal is connected from the from Chebyshev Low Pass filter to amplifier. Event:The Switch is in position B GOTO: EQ slide switch in position B State: EQ slide switch in position B Event: The Switch is in position A GOTO: EQ slide switch in position A Event: The Switch is in position B # Signal is connected from the from Chebyshev Low Pass filter to the 3 band EQ, then the amplifier. | This are accurate which is great but the infromation it captures is trivial. Lets talk about what is the best way to capture this information.
Malcolm Knapp | Product Definition.txt | d7b8fe0 | Arduino <--> Computer Interface command list is missing | enumerate the commands you want to be able to send, if any. If you are not going to send any commands the remove this Command Definition