## Professionalism
The Engineer Accelerator
Session | ENTER DATE
Professionalism
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes | Derek Meng
Review, Release, Version Control Lists
Choose a task list format
Task enumeration for Product Definition

## Hardware Development Process
The Engineer Accelerator
Session | Independent
Hardware Development Process
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes | Estimated Hours | Actual Hours
Flow Diagram | 1 | 2017-05-22 | 2017-05-24 | End of Day
Functionality Definition.txt | 1 | 2017-05-22 | 2017-05-24 | End of Day
Major Components BOM | 2 | 2017-05-25 | 2017-06-01 | End of Day
Hardware Block Diagram | 2 | 2017-05-25 | 2017-06-01 | End of Day
Product Architecture | 2 | 2017-05-25 | 2017-06-01 | End of Day
Estimate Architecture Task Hours
Estimate Task Hours
Eagle Library
Eagle Schematic
Eagle Layout
Cable Definition (if cables are needed in your design)
Feature and Behavior Acceptance criteria
Enter Hours Spent
Enter Hours Spent
Board Bring Up
Board Fab and Build
Full BOM
Manufacturing Package
Estimate Task Hours
Enter Hours Spent
Portoflio
Presentation