## Professionalism
The Engineer Accelerator
Session | Summer 2017
Professionalism
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes
Review, Release, Version Control Lists | 1 | 2017-07-05 | 2017-07-19 | 6:00pm
Choose a task list format | 1 | 2017-07-05 | 2017-07-19 | 6:00pm

## Hardware Development Process
The Engineer Accelerator
Session | Independent
Hardware Development Process
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Extension Due Date | Complete | Notes | Estimated Hours | Actual Hours
Flow Diagram | 1 | 2017-05-22 | 2017-05-24 | End of Day
Functionality Definition.txt | 1 | 2017-05-22 | 2017-05-24 | End of Day
Major Components BOM | 2 | 2017-05-25 | 2017-06-01 | End of Day
Hardware Block Diagram | 2 | 2017-05-25 | 2017-06-01 | End of Day
Product Architecture | 2 | 2017-05-25 | 2017-06-01 | End of Day
Source Parts | 4 | 2017-06-08 | 2017-06-19 | End of Day
Feasibility Study | 4 | 2017-06-08 | 2017-06-19 | End of Day
Code Hello World | 4 | 2017-06-08 | 2017-06-26 | End of Day
Solder Perf Board Prototype | 4 | 2017-06-28 | 2017-07-01 | End of Day | 2017-07-10
Summer Session
RemotePi App Tested | 1 | 2017-07-05 | 2017-07-08 | Beginning of Class
GUI Implementation | 1 | 2017-07-05 | 2017-07-08 | Beginning of Class
Extend GUI | 2 | 2017-07-08 | 2017-07-10 | End of Day
Sewing the Hat | 2 | 2017-07-08 | 2017-07-10 | End of Day
Read through Eagle Tutorials | Spring 3 | 2017-05-30 | 2017-06-05 | 2:00pm | 2017-07-22
Eagle Setup | Spring 3 | 2017-05-30 | 2017-06-05 | 2:00pm | 2017-07-22 | ?
Display Sourcing | 4 | 2017-07-22 | 2017-07-25
Display Test | 4 | 2017-07-22 | 2017-07-31
Eagle Schematic | 4 | 2017-07-22 | 2017-07-27
Eagle Layout | 4 | 2017-07-22 | 2017-08-01
Board Cut | 4 | 2017-07-22 | 2017-08-03
PCB Assembly | 4 | 2017-07-22 | 2017-08-07
PCB Bring Up | 4 | 2017-07-22 | 2017-08-11 |  |  |  | Delayed to summer session
Display GUI Bring Up | 4 | 2017-07-22 | 2017-08-25
Enter Hours Spent
Board Bring Up
Board Fab and Build
Full BOM
Manufacturing Package
Estimate Task Hours
Enter Hours Spent
Portoflio
Presentation