## Sheet1
Author | Malcolm Knapp
Date | 2017-05-17
Project | Arduino DDS Extension
Reviewer | Document | Version | Issue | Suggestion | Documentation Updated | Issue | Documentation Updated
Malcolm Knapp | Product Definition | 2b6f39 | versioning on file name is unecessary | github handles versioning so you can delete that. | Documents name changed to Product Definition.txt
Malcolm Knapp | Product Definition | 2b6f39 | The extra space looks messy | Remove extra spaces | Extra spaces removed
Malcolm Knapp | Product Definition | 2b6f39 | misspelled words | It is easy to do a spell check so do one before you submit | Spell checker run
Malcolm Knapp | Product Definition | 2b6f39 | "- State one passes signal from LPF to the Attenuator - State two passes signal through EQ. " is capture by the Flow Diagram | remove from the text file | Text removed from the file
Malcolm Knapp | Product Definition | 2b6f39 | " - Variable resitors on each filters output to control amplitude " Why do you need this when there is a master Attenuator? | Determine if they are redundent or not | Not redundent. Vocabulary is changed to make it more clear. Variable resistors attached to each filters output to control the individual band amplitude
Malcolm Knapp | Product Definition | 2b6f39 | On the BLE the " 3.3V input" over is an over definition. | Determining voldtage for components usually can happen in the Architecture phase. You may end up finding a module that runs off 5V and so you would then have to change the this definition. What you are looking for is information that will not change throughout the how development | Removed the 3.3V
Malcolm Knapp | Product Definition | 2b6f39 | Phone Interface - Is this an inferface on a feature? | if it is an interface then move it to that section | Removed because it is not a feature, application would be a feature.
Malcolm Knapp | Product Definition | 2b6f39 | Do you just need a phone to communicate? | Think about what other things you need to communicate with a phone | Removed phone. Replaced with computer and wire to arduino
Malcolm Knapp | Product Definition | 2b6f39 | "- Wire from header to chip" is a lower level detail | you do not need to show this at the Product Definition level. You will get into that at the Architecture level | Removed the detail.
Malcolm Knapp | Product Definition | 2b6f39 | "- Must be modern version of bluetooth" is vague | How a about must be "Bluetooth Version > ???" | Removed the Bluetooth module
Malcolm Knapp | Product Definition | 2b6f39 | " State: Eq switch off The State Switch has been deactivated" I am unclear how the state are organized between the two switches. Are they parallel states or do they interact. | Clarify what you mean by this | Changed to "The Switch is in position 0" and the atates are in parallel
Malcolm Knapp | Product Definition | 2b6f39 | "FEATURE 3 Shield Connection" is describing an interface not a Feature | move it to the feature section and combine it with the Bluetooth Interface | Shield connection is moved into the interface section
Malcolm Knapp | Product Definition | 2b6f39 | "FEATURE 4 Arduino Channel Selector" characteristics does not match flow diagram | Decide on what connections you want and update the appropriate places | Multiple signals from the arduino are split between separate channels.
Malcolm Knapp | Flow Diagram | 2b6f39 | It is a little cramped | In Inkscape you have an infinite page so you it to make your flow diagrams easy to read. Align the main signal in one row and then have the secondard signal come off of that. See 012916 Flow Diagram Organization for details | More spaces added. | What I was trying to get at was to align and organize the block diagram so it is easier to read.
Malcolm Knapp | Flow Diagram | 2b6f39 | FOR ALL other notes see Feature Block Diagram Rev_3_5-16-2017 - MK Comments |  | Comments addressed
Malcolm Knapp | Flow Diagram | 2b6f39 | No computer block | add this block | Added computer block
Malcolm Knapp | Flow Diagram | 2b6f39 | EQ switch called Switch | Synchronize Names | Synchronized to EQ sqitch
Malcolm Knapp | Flow Diagram | 2b6f39 | Connection between BLE and microcontroller missing | Add Connection | Reomved the BLE module
Malcolm Knapp | Flow Diagram | 2b6f39 | Code flow diagram is missing | Add Code Flow diagram for Tone to DDS path | Product definition Product States is text version of code flow | The flow of information in within the ATTiny has not been enumerated yet
Malcolm Knapp | All docs | cbdf8ef | Auther, date etc not updated | Make sure you update author and date
Malcolm Knapp | Major Signals | cbdf8ef | "Arduin pin XX" is not descriptive. Same with LED Signal | Choose a more descrptive name
Malcolm Knapp | Major Signals | cbdf8ef | Are you sure the DDS signal max freq is 50Khz?
Malcolm Knapp | Major Signals | cbdf8ef | Make sure that max frequency is what you are calling out and not fundamental | Adjust as needed
Malcolm Knapp | Major Signals | cbdf8ef | Why is the LED Signal frequecny 20Hz
Malcolm Knapp | Major Signals | cbdf8ef | Arduino Output Signal | Do you mean the Tone Signal?
Malcolm Knapp | Interface List | cbdf8ef | "Dip_1, Dip_2, etc" are not descriptive names | Choose a more descriptive name for this signal
Malcolm Knapp | Interface List | cbdf8ef | Attiny does not have all pins called out | Add missing pin out
Malcolm Knapp | Interface List | cbdf8ef | Pin Numbers are not numbers | Replace with number. The INTERFACE NAME is where you put the connector name and when you do choose a descriptive name
Malcolm Knapp | Current Budget | cbdf8ef | Why does the EQ pull current
Malcolm Knapp | Major Components BOM | cbdf8ef | LED is available from mouser. | Can you get it from Mouser or do you need to get it from Digikey
Malcolm Knapp | Major Components BOM | cbdf8ef | Speaker is .1W but Speaker Single in is .125W | Will this be a problem?
Malcolm Knapp | Major Components BOM | cbdf8ef | Lots of parts are through hole. How will that impact manufacturabiility | Surface mount parts are easier to use with a milled board so consider that when choosing parts
Malcolm Knapp | Major Components BOM | cbdf8ef | Speaker has a bandwidth of 200Hz to 20KHz not 20Hz to 20KHz | Is that a problem?
Malcolm Knapp | Calculations | cbdf8ef | Caluclations are not specific | Make eachcalculations speicific. It is fine to duplicate the equations. This means if something changes you do not destroy information used by other parts of the design
Malcolm Knapp | Calculations | cbdf8ef | Amplifier Calculations. How much applification are you planning to have | Add Calculations
Malcolm Knapp | Calculations | cbdf8ef | Filter loading calculations. How much signal loss happens in the filters | Add Calculations
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | Overall great job on this diagram. Is a easy to read and well laid out
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | Major signal names missing | Add the major signal names
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | How will the ATTINY be programed | Add a programming method
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | There is no master volume control in this diagram. | Is that intensional?
Malcolm Knapp | Hardware Block Diagram | cbdf8ef | how will the 3 band EQ be implemented. If it is in separate filters thet should be shown as separate blocks | Add blocks as needed