## Professionalism
The Engineer Accelerator
Session | Summer 2017
Professionalism
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes
Review, Release, Version Control Lists | 1 | 2017-07-05 | 2017-07-19 | 6:00pm
Choose a task list format | 1 | 2017-07-05 | 2017-07-19 | 6:00pm

## Hardware Development Process
The Engineer Accelerator
Session | Independent
Hardware Development Process
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Extension | Notes | Estimated Hours | Actual Hours
Flow Diagram | 1 | 2017-05-22 | 2017-05-24 | End of Day
Functionality Definition.txt | 1 | 2017-05-22 | 2017-05-24 | End of Day
Major Components BOM | 2 | 2017-05-25 | 2017-06-01 | End of Day
Hardware Block Diagram | 2 | 2017-05-25 | 2017-06-01 | End of Day
Product Architecture | 2 | 2017-05-25 | 2017-06-01 | End of Day
Source Parts | 4 | 2017-06-08 | 2017-06-19 | End of Day
Lab Tools list | 4 | 2017-06-08 | 2017-06-19 | End of Day
Feasibility Study | 4 | 2017-06-08 | 2017-06-19 | End of Day
Code Hello World | 4 | 2017-06-08 | 2017-06-26 | End of Day
Solder Perf Board Prototype | 4 | 2017-06-28 | 2017-07-01 | End of Day | 2017-07-10
Summer Session
RemotePi App Tested | 1 | 2017-07-05 | 2017-07-08 | Beginning of Class
GUI Implementation | 1 | 2017-07-05 | 2017-07-08 | Beginning of Class
Extend GUI | 2 | 2017-07-08 | 2017-07-10 | End of Day
Sewing the Hat | 2 | 2017-07-08 | 2017-07-10 | End of Day
Read through Eagle Tutorials | 3 | 2017-05-30 | 2017-06-05 | 2:00pm |  | Delayed to summer session
Eagle Setup | 3 | 2017-05-30 | 2017-06-05 | 2:00pm |  | Delayed to summer session
Eagle Library
Eagle Schematic
Eagle Layout
Cable Definition (if cables are needed in your design)
Feature and Behavior Acceptance criteria
Enter Hours Spent
Enter Hours Spent
Board Bring Up
Board Fab and Build
Full BOM
Manufacturing Package
Estimate Task Hours
Enter Hours Spent
Portoflio
Presentation