## Professionalism
The Engineer Accelerator
Session | Summer 2017
Professionalism
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes
Review, Release, Version Control Lists | 1 | 2017-07-05 | 2017-07-19 | 6:00pm
Choose a task list format | 1 | 2017-07-05 | 2017-07-19 | 6:00pm

## Hardware Development Process
The Engineer Accelerator
Session |  | Independent | Summer 2017
Hardware Development Process
Deliverables Tracking |  | Class Assigned | Assigned | Due Date | Time | Notes | Zacher Tiburzi | Estimated Hours | Actual Hours
Flow Block Diagram |  | 1 | 2017-05-13 | 2017-05-16 | End of Day
Product Definition.txt
| Characteritics List | 1 | 2017-05-13 | 2017-05-16 | End of Day
| Behavior Definition | 1 | 2017-05-13 | 2017-05-16 | End of Day
| Interface list | 1.5 | 2017-05-16 | 2017-05-19 | End of Day
Major Components BOM |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Hardware Block Diagram |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Product Architecture |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Fill in Task Enumeration for Product Definition |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Estimate Architecture Task Hours
Make update to Architecture |  | 3 | 2017-05-24 | 2017-05-30 | End of Day
Estimate Task Hours |  | 3 | 2017-05-24 | 2017-06-26 | End of Day
Eagle Library |  | 3 | 2017-05-24 | 2017-06-26 | End of Day
Eagle Schematic |  | 3 | 2017-05-24 | 2017-07-08 | Beginning of Class
Eagle Layout Current Progress |  | 3 | 2017-05-24 | 2017-07-12 | Beginning of Class
Cable Definition (if cables are needed in your design) |  | NA | NA | NA | NA
Eagle Layout Cut Ready |  | 5 | 2017-07-08 | 2017-07-22 | Beginning of Class
Feature and Behavior Acceptance criteria
Enter Hours Spent
Enter Hours Spent
Board Bring Up
Board Fab and Build
Full BOM
Manufacturing Package
Estimate Task Hours
Enter Hours Spent
Portoflio
Presentation