## Sheet1
Name
Project
Phase | Task | Sub Task | Number | Per Task | Estimate | Actual | Units | Amount Assigned | Effciency | Duration
Product Definition |  |  |  |  | 2
| Brainstorming |  |  |  | 2
| Research |  |  |  | 2
| Design Analysis |  |  |  | 4
| Flow Diagram |  |  |  | 2
| Learning* |  |  |  | 2
| Characteristics List |  |  |  | 2
| Behavior Definition |  |  |  | 2
Interface List
Architecture
| Source |  | 10 | 1 | 10
| Major Compnents BOM |  |  |  | 2
| HW Block Diagram |  |  |  | 3
| Datasheet Research |  |  |  | 8
Product Architecture
|  | Calculations |  |  | 4
|  | Current Budget |  |  | 3
|  | Major Signals List |  |  | 2
|  | Interface Pinouts |  |  | 4
Realization
| Prebuilt Eagle library Research |  |  |  | 4
| Eagle library build |  |  |  | 3
Device
Package
Symbol
| Eagle schematic |  |  |  | 3
Place
Wire
Naming
Error Checking
| Eagle Layout |  |  |  | 2
Bring Up
Test