## Sheet1
Name
Project
Phase | Task | Sub Task | Number | Per Task | Estimate | Actual | Units | Amount Assigned | Effciency | Duration
Product Definition | [9 empty] | 1 Week
| Brainstorming |  |  |  | 2 |  | Hours
| Research |  |  |  | 2 |  | Hours
| Design Analysis |  |  |  | 4 |  | Hours
| Flow Diagram |  |  |  | 2 |  | Hours
| Learning* |  |  |  | 2 |  | Hours
| Characteristics List |  |  |  | 2 |  | Hours
| Behavior Definition |  |  |  | 2 |  | Hours
| Interface List |  |  |  | 2 |  | Hours
Architecture | [9 empty] | 2 Weeks
| Source |  | 10 | 1 | 10 |  | Hours
| Major Compnents BOM |  |  |  | 2 |  | Hours
| HW Block Diagram |  |  |  | 3 |  | Hours
| Datasheet Research |  |  |  | 8 |  | Hours
Product Architecture
|  | Calculations |  |  | 4 |  | Hours
|  | Current Budget |  |  | 3 |  | Hours
|  | Major Signals List |  |  | 2 |  | Hours
|  | Interface Pinouts |  |  | 4 |  | Hours
Realization | [9 empty] | 4 Weeks
| Prebuilt Eagle library Research |  |  |  | 4 |  | Hours
| Eagle library build |  |  |  | 3 |  | Hours
|  | Device |  |  | 2 |  | Hours
|  | Package |  |  | 2 |  | Hours
|  | Symbol |  |  | 2 |  | Hours
Eagle schematic
|  | Place |  |  | 2 |  | Hours
|  | Wire |  |  | 2 |  | Hours
|  | Naming |  |  | 2 |  | Hours
|  | Error Checking |  |  | 2 |  | Hours
Eagle Layout
|  | Place |  |  | 3 |  | Hours
|  | Wire |  |  | 3 |  | Hours
|  | Naming |  |  | 2 |  | Hours
|  | Error Checking |  |  | 3 |  | Hours
Bring Up | [9 empty] | 2 Weeks
Asemble
|  | Layout | 0.5 | 30 | 15 |  | Hours
|  | Relayout | 0.5 | 20 | 10 |  | Hours
Test
|  | Multimeter | 0.05 | 30 | 1.5 |  | Hours
|  | Oscilliscope | 0.05 | 30 | 1.5 |  | Hours
|  | Arduino |  |  | 2 |  | Hours
Test | [9 empty] | 2 Weeks
|  | Arduino |  |  | 4 |  | Hours