## Professionalism
The Engineer Accelerator
Session | Summer 2017
Professionalism
Deliverables Tracking | Class Assigned | Assigned | Due Date | Time | Notes
Review, Release, Version Control Lists | 1 | 2017-07-05 | 2017-07-19 | 6:00pm
Choose a task list format | 1 | 2017-07-05 | 2017-07-19 | 6:00pm

## Hardware Development Process
The Engineer Accelerator
Session |  | Independent | Summer 2017
Hardware Development Process
Deliverables Tracking |  | Class Assigned | Assigned | Due Date | Time | Status | Notes | Extension
Flow Block Diagram |  | 1 | 2017-05-13 | 2017-05-16 | End of Day
Product Definition.txt
| Characteritics List | 1 | 2017-05-13 | 2017-05-16 | End of Day
| Behavior Definition | 1 | 2017-05-13 | 2017-05-16 | End of Day
| Interface list | 1.5 | 2017-05-16 | 2017-05-19 | End of Day
Major Components BOM |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Hardware Block Diagram |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Product Architecture |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Fill in Task Enumeration for Product Definition |  | 2 | 2017-05-16 | 2017-05-23 | End of Day
Make update to Architecture |  | 3 | 2017-05-24 | 2017-05-30 | End of Day
Eagle Library |  | 3 | 2017-05-24 | 2017-06-26 | End of Day
Eagle Schematic |  | 3 | 2017-05-24 | 2017-07-08 | Beginning of Class
Eagle Layout Current Progress |  | 3 | 2017-05-24 | 2017-07-12 | Beginning of Class
Cable Definition (if cables are needed in your design) |  | NA | NA | NA | NA
Eagle Layout Cut Ready |  | 5 | 2017-07-08 | 2017-07-22 | Beginning of Class |  |  | 2017-07-24
Board Fab and Build |  | 6 |  | 2017-08-05 | End of Class
Board Bring Up |  | 6 |  | 2017-08-05 | End of Class
Full BOM
Manufacturing Package
Enter Hours Spent
Portoflio
Presentation